## Phasing and Work
DRAFT IN PROGRESS- Association Level Planning for Reopening after Stay Home Stay Safe Order is Lifted for YMCA's in NC/Buncombe County
Centers to develop their specific planning documents while resourcing this document with metro support
YMCA of Western North Carolina
First Draft: 4/21/2020
Last Updated: 4/27/2020
Optimistic Goal- Open Facilities by May 15th and be ready to open sooner if possible
Categiry | Phase | Task/Info | Owner | Completed | Notes | Cost to be added
General |  |  | Team
| P1 | Develop/Maintain a Plan for a potential second wave of closure | Team
| P1 | Order and distribute Masks for staff only in case necessary | Bryan | Limited supply in Assoc. Ordered 4000 on 4/21 (2 wk lead time). | https://www.safetyconnexion.com/
| P1 | Order and distribute Thermometers. For staff screening pre shift. | Bryan | Limited supply in Assoc. Ordered 40 on 4/21; two separate orders of 20 (2 wk lead time). | https://wyze.com/
| P1 | Ensure adequate supply of Cleaning Chemicals and instructions/training/ppe for how staff/members use them | Property Director | Current supply onsite for opening.
| P1 | Ensure Adequate Cleaning Chemicals supply for Rightway Cleaning | Property Director | Current supply onsite for opening.
| P1 | Order and distribute first 1-2 months of Hand sanitizer (Centers have current supply for early days before delivery if necessary) | Bryan | Current supply onsite for opening. Ordered 2 pallets on 4/21/2020 (2 wk lead time); last Centers 2 months and all Camp; 3 year shelf life | FelxPac
| P1 | All chemical dispensers labeled and SDS system in place | Property Director
| P1 | Ensure adequate supply of Gloves for staff cleaning measures | Property Director
| P1 | Sneeze Shields or build in social distancing spacing in transactional areas per center spaces | Exec
| P1 | Spacing and Capping/Max Occupancy Data for Centers/Spaces - Process to comply per Center | Governor/Team
| P1 | Verify all first aid kits are in place and replenish and/or re-stock as necessary. | Exec
| P1 | Confirm that all AED and Life Safety equipment is in place and operable. | Exec
| P1 | Test of all computers, laptops, printers and other electronics that were taken off-line. Reconfigure or reinstall as warranted. | Exec/IT
| P1 | Check security cameras and recording devices to verify operability. | Exec/IT
| P1 | Reset the telephone messaging to previous (or new) hours of operations, referencing new programs or important updates. | Exec/IT
| P1 | Update temporary posted signage regarding impending re-opening schedule, and review permanent building signage for adjustment (if operational hours will be modified). Upon opening, remove all temporary communication pieces. | Exec
| P1 | Update all communication boards throughout the YMCA, ensuring membership material and communication is updated for the re-opening. | Exec
| P1 | Update all exterior signage and messaging systems as warranted. | Exec
| P1 | Center walkthroughs to create center specific plans | Bryan,Jen, Exec
General Phase Info | P1 | Phase 1 | Team
| P1 | · Staff
| P1 | o Temperature checks required
| P1 | o Screening questionaire completed
| P1 | o Personal protective equipment required (masks only)
| P1 | o Additional cleaning shifts added for member areas
| P1 | o Required to wash hands at the beginning and end of shift
| P1 | · Members
| P1 | o One entrance to the facility (only the back door of Reuter)
| P1 | o Screening Limitation signage on the door
| P1 | o If you present as sick (coughing, sneezing) you will be asked to leave
| P1 | · Facility
| P1 | o Adjusted operating hours/locations in line with potential long-term plans or as needed to match staffing.
| P1 | o Traffic flow or enter/exit designations if necessary to control narrow hallways (location differences)
| P1 | o Prop open doors when possible to create no touch walkways
| P1 | o Protective screens & additional hand sanitizer dispensers
| P1 | o Additional cleaning supplies available to members to pick up and take with them as they workout (spray bottle, paper towels)
| P1 | o Water Fountains for bottle fill only
| P1 | o Locker rooms open, no showers (signs on lockers for distancing)
| P1 | o Pools closed
| P1 | o No steam, sauna or hottubs
| P1 | o No pickleball/ racquetball
| P1 | o No game play in the gymnasium – bring your own ball
| P1 | o YDC and Kid Zones closed
| P1 | o Signage
| P1 | § Screening limitations
| P1 | § Hand washing
| P1 | § 6 feet
| P1 | § How to clean – spray and let it stay
| P1 | § If you present as sick (coughing, sneezing) you will be asked to leave
| P1 | · Wellness Programing
| P1 | o Reservations system for the wellness floor will be considered
| P1 | o Equipment will be limited or moved to create social distancing
| P1 | § If possible equipment in use will be rotated mid-day to allow additional deep cleaning
| P1 | § Fans will not run to circulate air.
| P1 | § Spots will be marked in free weight areas for members to use
| P1 | o Members must disinfect equipment before and after use (spray bottles at each)
| P1 | o GE classes reduced and capped
| P1 | § Reservations online only for all classes
| P1 | § Class times adjusted and schedules updated!
| P1 | § Spots marked on the floor
| P1 | § Limit use of equipment when possible – only equipment that can be sanitized
| P1 | § Schedule spread out to create clean time and avoid member waiting areas
| P1 | o Virtual GE classes will continue
| P1 | o Virtual personal training and programing will continue
| P1 | o Coaching appointments will be available virtually
| P1 | o No Small group classes or paid programing
| P1 | · Youth Programing
| P1 | o YDC and Kid Zones closed
| P1 | o No PNO, PMO, or youth sports or arts programing
| P1 | o No swim lessons or swim team
| P1 | · Services
| P1 | o No towel services
| P1 | o No coffee services
| P1 | o No guest access
| P1 | o Seating and lobby areas reduced for minimal needs of members not for socializing.
| P1 | o LESS PAPER AND PENS at the desk, get systems online directly.
| P2 | Phase 2 (changes to Phase 1) | Exec
| P2 | · Staff -no changes
| P2 | · Members
| P2 | o Additional entrances reopen
| P2 | · Facility
| P2 | o Locker rooms and shower areas open (stalls reduced for distancing, signs on lockers for social distancing)
| P2 | o Pools open if permits are available
| P2 | § 1 person per lap lane (reservation system for 30 min max)
| P2 | § No pool “toys”
| P2 | § Participants limited by SF and LG ratios
| P2 | § Sitting areas controlled for social distancing
| P2 | o YDC and Kid Zone open (see below) with limited numbers and hours
| P2 | o Pickleball / racquetball return if social distancing can be met and facility space is available
| P2 | o Group play in the gymnasium limited to small gatherings
| P2 | · Wellness Programing
| P2 | o Fans can circulate air
| P2 | o GE classes increase and numbers adjust with local requirements
| P2 | o Potential to move virtual classes under membership (password, scan requirement, service provider?)
| P2 | · Youth Programing
| P2 | o YDC and Kid Zones open, numbers limited/member time reduced to one hour
| P2 | § Numbers will align with current state or local guidelines (i.e. 10 total or 36 sf per person)
| P2 | § Reservation system in place to accommodate members
| P2 | § Temperature checks for all kids, hand washing/sanitizing required upon entry and exit
| P2 | o Swim Team returns to practice? (phase 2 or 3)
| P2 | § Temperature checks for all participants
| P2 | § Adjusted practice times to reduce team interactions
| P2 | § Reduced swimmers in lanes to X
| P2 | § Come prepared for practice and leave directly from deck- locker room use limited to restroom needs
| P2 | § Only parents allow to attend meets, parents asked to wait in cars instead of in the facility (I believe they are already not allowed on deck during practice).
| P2 | o Youth swim lessons return for private lessons only
| P2 | · Services
| P2 | o Seating areas will return with social distancing
| P2 | o Coffee considered
| P3 | Phase 3 (changes to phase 2) | Exec
| P3 | · Staff
| P3 | o Personal protective equipment advised not required
| P3 | · Members
| P3 | · Facility
| P3 | · Wellness Programing
| P3 | o GE classes by registration and walk in, but numbers still capped to align with state guidelines
| P3 | o Coaching appointments will be available virtually and in person
| P3 | o Personal training and small group programing will resume if social distancing can be met
| P3 | · Youth Programing
| P3 | o Selected youth programing returning (some programing will not return)
| P3 | o Unlicensed center Youth camps guidelines will align with suggested association camp changes for health checks, hand washing, group size limits etc.
| P3 | o Youth Sports
| P3 | § Temperature checks for all participants and coaches
| P3 | § Hand sanitizer available on site
| P3 | § Only parents of participants and coaches permitted to attend practices and games – no guests
| P3 | § Social distancing required (inside and outside)
| P3 | § Equipment cleaned before/after and during play as possible
| P3 | § Soccer “throw-ins” will be “kick-ins”?
| P3 | § Offsite restrooms instructed to be one in/ one out
| P3 | o Youth Swim Lessons return
| P3 | § Temperature checks for participants
| P3 | § Number of lessons held at one time reduced
| P3 | § Family members limited on deck and required to
| P3 | · Services
| P3 | o Coffee resumes
| P3 | o No towel service (not bringing this back)
Continue to Add OTHER NECESSARY TASKS/INFO
Finance |  |  | Sabra
|  | Insurance Change Back/Communications | Sabra
|  | Vendor notification regarding reopening timeline | Dawn
|  | Loans/Grants assessment/compliance | Sabra
|  | Forecast new expenses via related leadership and staff communications | Sabra
|  | Cost conscious guidelines distributed to staff | Sabra
Continue to Add OTHER NECESSARY TASKS
Membership/YBC |  |  | Jen, Gay, Sabra
Plan and Implement Phased Approach
|  | Staff training considering new variables | Exec
|  | Prep for and Implement staffing plan for updated operations | Exec
|  | Conversica Assessment and Implementation | Jen
|  | Strategy to generate sales and get our members back (including cancellations) | Jen
|  | Draft update (holds back online) | Gay
|  | Welcome back templates/communications | MaryO
|  | Post first visit communications/recognition/survey | Jen
|  | Touchless transactions | Jen
Continue to Add OTHER NECESSARY TASKS
Healthy Living |  |  | Jen
Plan and Implement Phased Approach
|  | Staff training considering new variables | Exec
|  | Prep for and Implement staffing plan for updated operations | Exec
|  | Equipment layout assessment/modification | Exec
|  | Group Ex. Schedule assessment/testing/modification | Exec
|  | Reservation platform(s) implemented | Jen
|  | Maintain balance of virtual offerings | Exec
Continue to Add OTHER NECESSARY TASKS
Human Capital |  |  | Anette
Plan and Implement Phased Approach
|  | Staff expectations/awareness communications prior to opening | Anette
|  | Remote Onboarding Process Implemented | Anette
|  | Exec Support Measures | Anette
|  | BLS changes implemented temporarily | Bryan and Anette
Continue to Add OTHER NECESSARY TASKS
Youth Development |  |  | Melissa/Will
Plan and Implement Phased Approach
|  | Prep for and Implement staffing plan for updated operations | Melisa
|  | Remote and in-person Training planning/implementation | Melissa
|  | Supply Refresh/procurement for cleaning, crafts, etc correlating with the reducing virus spread | Will
|  | PPE for staff as required for licensing/county for all sites (including unlicensed sites). | Will
Wipe down and clean all program toys, shelving, desks, tables, storage, etc.
Continue to Add OTHER NECESSARY TASKS
Marketing and Communications |  |  | MaryO
|  | Support work above | MaryO
|  | Welcome back strategy/announcement | MaryO
|  | Continued member communication related to new/updated operations | MaryO
|  | Recognize members who stuck with us | MaryO
|  | Donor communications | MaryO
|  | Program Participant communications | MaryO
|  | Competitor awareness to include in decision making process and communications | MaryO
|  | Strategies to reengage with members | MaryO
|  | Communications to support staffs response to member FAQ’s/concerns | MaryO
Continue to Add OTHER NECESSARY TASKS
Occupancy |  |  | Exec
|  | GENERAL | Property Director
Plan and Implement Phased Approach
Prepare Center for social distancing measures
Remove any installed temp barricades, locks, and property security installed during closure
Prior to reopening, review all steps taken and measures enacted during closure, and assess impact on facility operations
Conduct a walk-through of property for any possible damage and/or facility concerns; photograph and report as necessary. Communicate any security breaches or risk management issues with the facility to insurance providers.
Test all building systems (mechanical, plumbing, and electrical) and allow ample time (24-48 hours) to ensure temperature set points are re-established.
Waste and recycling (dumpsters) should be restored and inspected for immediate service needs.
Reactivate (as warranted) all suspended or cancelled contracted services such as landscaping, janitorial, pest control, etc. Make contract adjustments as warranted.
If all occupancy work was suspended, a full cleaning and sanitation of the facility should be performed to ensure safe occupancy after temporary shut down.
Contact any vending contractors to schedule vending machine restocking, etc.
Inspect all ceilings and HVAC ventilation grills. High-level dusting may be necessary after mechanical service reduction and should be addressed accordingly.
Consider running water and testing all restroom toilets, urinals and sinks to remove waterline debris and clear drains.
Consider priming floor drains and all plumbing equipment (toilets, sinks, showers, etc.) to ensure operability.
|  | BUILDING SYSTEMS | Property Director
HVAC:
Adjust temperature set points for all facility air handling units for general occupancy.
Inspect air filters and clean or change as warranted.
ELECTRICAL:
Inspect all emergency building and site/parking area lighting and monitor any battery back up.
Adjust any breaker and panel disconnect as needed for facility operations.
PLUMBING:
Inspect and adjust all water heating units to set points for normal building operations.
FIRE PROTECTION/LIFE SAFETY:
Confirm that smoke and fire sensors are operable.
Inspect the warranty and dates on all fire extinguishers.
Confirm that fire suppression systems remain operable and meet all local inspection requirements.
Update all MSDS Sheets.
ELEVATOR/LIFT:
Test and operate all lifts and elevators for operational effectiveness.
Clean and sanitize all interior and exterior walls, door panel, buttons, railings, etc.
Sweep, vacuum or mop all floor surfaces.
LIGHTING:
Check all lighting timers (parking lot, occupancy, etc.) and reset as warranted.
Clean light fixtures throughout, replacing bulbs and ballasts as needed.
Inspect all lighting to ensure all lights are functional after several week shut down, including parking lots and emergency and general occupancy lighting.
Clean and sanitize all light switches throughout the facility.
WINDOWS/GLAZING:
Clean all glass surfaces, inside and outside, with special focus on high touch glass. Ensure staff is updating sanitation of these critically sensitive areas (front doors, child watch, multipurpose, etc.).
|  | BUILDING VENUES | Property Director
Refill or install hand sanitation station at entrance, including waste container for wipes.
CHILD WATCH/CHILDRENS ADVENTURE CENTER:
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points.
Add exterior hand sanitation areas and waste collection for sanitizing wipes.
COMMUNITY/MULTIPURPOSE ROOM/CONFERENCE ROOMS:
Refill or install hand sanitation stations at workstations and near coffee bars, being sure to include waste containers for wipes.
KITCHEN(S) AND STAFF BREAK ROOM:
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points.
INDOOR TRACK, GYMNASIUM & SPORT COURTS:
Refill or consider installation of hand sanitation centers at entrances.
GROUP EXERCISE STUDIOS:
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points in the studio spaces.
Test all sound, A/V, TV, and speakers for functionality.
Clean and wipe all bikes and personal mats.
WELLNESS CENTER:
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points in the wellness center.
Consider installation of hand sanitation centers near water fountains and install sanitation signage.
Test all sound, A/V, TV equipment and speakers for operability.
ADULT LOCKERS, YOUTH LOCKERS, UNIVERSAL LOCKERS & RESTROOMS:
Check all auto flushers for operations and repair or adjust as warranted.
Replace and replenish all paper products as warranted.
Replace and replenish all soap and shampoo. Sanitize all dispensers and consider installation of automatic dispensers if possible.
Refill or consider installation of hand sanitation near water fountain and safety sanitation signage.
If only hand dryers are available; consider adding paper towels and waste receptacles to improve hand sanitation after turning on and off water.
AQUATIC CENTER:
A certified pool operator should inspect the pool and its related systems daily. Chemical quantities should be inspected and adjusted, as needed. Additionally, the pool filtration system may require backwashing, especially if the pool is outdoors, depending on the loading and type of filter system.
Confirm chemical delivery for ongoing operations.
If necessary, confirm gas delivery as warranted.
Pertaining to steam rooms, saunas and whirlpools, whether located within locker rooms or on pool decks, power on, test and set temp set points. Ensure facilities are clean and sanitized and check for mold and mildew growth.
Ensure that minimum disinfectant residuals, per local/state code, are maintained within the pool water because the pool was unoccupied.
For indoor aquatic facilities, inspect the HVAC/DX system to adjust to normal operations.
Inspect all door gates, security measures.
Inspect and adjust water levels in each pool tank as warranted.
Inspect, test all filtration system operations.
|  | PROPERTY AND GROUNDS | Property Director
Consider walking parking area for trash, clean and sweep parking lot as warranted.
Evaluate the maintenance of landscape, exterior grounds, any athletic fields and parking areas and schedule cutting, mulching, pruning and installation of annuals and evaluate for overall curb appeal.
Test and run all irrigation systems and re-establish timers as warranted.
Inspect and empty all exterior trash receptacles, replacing liners as warranted.
Inspect, reinstalling if necessary, any exterior furnishings, e.g., benches, tables, chairs, field equipment, and pool area furniture.
If applicable, ensure all property gates, external storage and out-buildings are secured.
Inspect, water and replenish any living indoor plants, planters, green wall systems/vertical gardens, etc.
Inspect and secure any external buildings, fencing, storage and out-buildings.
Inspect any vehicles/fleets kept on-site. Test start all engines. Restock all vehicles with occupancy valuables such as life safety, vehicle travel logs, etc. Consider timing of general maintenance needs as warranted.
Complete weekly inspection checklist.
Sweep busses.
Check all fluid levels.
Inspect windows for possible damage and leaks.
Inspect seats for seat belts and security (bolts, etc.).
Clean and sanitize seats, drivers' areas, doors, handles, seat backs, etc.
Check safety supplies (orange cone, wheel chocks, fire extinguisher, bus logs, etc.) and First Aid kits.

## Cleaning and Sanitize
BUILDING VENUES | Property Director
Lobby/Lounge
Clean and sanitize entry doors, door handles and entry glass (inside and outside).
Dust and wet mop all lobby floors, corridors, etc.
Clean and wipe down all lobby furniture.
Refill or install hand sanitation station at entrance, including waste container for wipes.
Clean and sanitize all high-touch areas including hand-rails, desktops and sides, check-in kiosks, front desk, and phone(s).
CHILD WATCH/CHILDRENS ADVENTURE CENTER:
Clean, wipe, and sanitize all door handles on all doors.
Clean, wipe, and sanitize all counter surfaces, changing stations, and other flat surfaces, focusing on high-touch areas.
Clean, wipe, sanitize and polish sinks, toilets, water coolers, and chrome fixtures.
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points.
Vacuum, damp mop, scrub and sanitize floors and baseboards.
Clean, wipe down and sanitize all waste receptacles inside and out, replacing liners as warranted.
Wipe down any common area furniture.
Clean, organize and sanitize storage areas, cupboards and closets.
Wipe down and clean all playground equipment.
Clean, wipe, sanitize and inspect all exterior playground water fountains.
Add exterior hand sanitation areas and waste collection for sanitizing wipes.
Clean any cribs, highchairs, etc.
Clean and sanitize all computers, keyboards or other high-touch administrative equipment as warranted.
COMMUNITY/MULTIPURPOSE ROOM/CONFERENCE ROOMS:
Clean and sanitize all doors, door handles and other high-touch areas, including copiers, fax machines, and mail distribution equipment.
Clean all door glass (inside and outside), including side lights.
Dust and vacuum all floors.
Clean and wipe down all desktops, chairs, chair arms, and miscellaneous furniture.
Refill or install hand sanitation stations at workstations and near coffee bars, being sure to include waste containers for wipes.
KITCHEN(S) AND STAFF BREAK ROOM:
Clean, wipe, and sanitize all door handles on all doors.
Clean, wipe, and sanitize all counter surfaces, tables, chairs, and other furniture.
Clean, wipe, and sanitize all wall surfaces, etc.
Clean, wipe, sanitize and polish all appliances, sinks, and stainless and chrome fixtures.
Clean, dust and test all hoods and ventilation fans.
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points.
Update sanitation and cleaning signage in studios for maintaining equipment.
Clean and sanitize all appliances and program equipment.
Clean all mirrored surfaces throughout.
Vacuum, damp mop, scrub and sanitize floors and baseboards.
Clean, wipe down and sanitize all waste receptacles inside and out, replacing liners as warranted.
Refill, wipe down and sanitize all flat surfaces, focusing on high-touch areas.
Clean, organize and sanitize storage areas, cupboards and closets.
INDOOR TRACK, GYMNASIUM & SPORT COURTS:
Dust mop all floor surfaces.
Clean, wipe, and sanitize all bleachers, benches and seating areas and all program equipment.
Clean, wipe, and sanitize all wall pads and all basketball backboards.
Refill or consider installation of hand sanitation centers at entrances.
GROUP EXERCISE STUDIOS:
Clean, wipe, and sanitize all door handles and door surfaces.
Clean, wipe, and sanitize all counter surfaces, ballet bars, and mirrored surfaces.
Wipe and sanitize all wall surfaces, etc.
Wipe, sanitize and polish water coolers and chrome fixtures.
Clean, dust and test all wall and floor fans.
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points in the studio spaces.
Update sanitation and cleaning signage in studios for maintaining equipment.
Clean and sanitize all small program equipment, mats, cardio, hand weights, weight racks, stools, benches and chairs.
Vacuum, damp mop, scrub and sanitize floors and baseboards.
Consider installation of hand sanitation centers near water fountains and install sanitation signage.
Clean, wipe down and sanitize all waste receptacles inside and out, replacing liners as warranted.
Refill, wipe down and sanitize all flat surfaces, focusing on high-touch areas.
Clean, organize, and sanitize storage areas and closets.
Clean and wipe all bikes and personal mats.
WELLNESS CENTER:
Clean, wipe, and sanitize all door handles and door surfaces.
Clean, wipe, and sanitize all counter surfaces and railings.
Clean, wipe, and sanitize all wall surfaces.
Clean, wipe, sanitize and polish water coolers, chrome fixtures.
Clean, dust and test all wall and floor fans.
Replace and replenish all sanitation wipes, towels, and paper products as warranted. Clean all dispensers and consider installation of new sanitation stations at all ingress and egress points in the wellness center.
Update sanitation and cleaning signage in wellness center for maintaining equipment.
Clean and sanitize all small fitness equipment, mats, cardio, hand weights, and wellness equipment.
Clean all mirrored surfaces throughout.
Vacuum, wet mop, scrub and sanitize floors and baseboards.
Consider installation of hand sanitation centers near water fountains and install sanitation signage.
Clean, wipe down and sanitize all waste receptacles inside and out, replacing liners as warranted.
Wipe down any common area furniture, stools, and benches.
Refill, wipe down and sanitize all cardio and selecterize equipment, focusing on high-touch areas.
Lift all cardio and wellness equipment and clean flooring and mats under each unit.
Clean and wipe all free weight racks.
Clean, organize and sanitize all desks and offices, focusing on high-touch surfaces.
Dust all electrical tracks and systems.
ADULT LOCKERS, YOUTH LOCKERS, UNIVERSAL LOCKERS & RESTROOMS:
Clean, wipe, and sanitize all door handles and door surfaces.
Clean, wipe, and sanitize all tile surfaces.
Clean, wipe, and sanitize all toilets, urinals, and shower partitions.
Clean, wipe, sanitize, and polish all fixtures, faucets and handles.
Check all auto flushers for operations and repair or adjust as warranted.
Clean, dust and test all wall and floor fans.
Replace and replenish all paper products as warranted.
Replace and replenish all soap and shampoo. Sanitize all dispensers and consider installation of automatic dispensers if possible.
Clean and sanitize all hair dryers or shared personal grooming equipment.
Clean all mirrored surfaces throughout.
Clean and sanitize all shower doors; curtains and replace as needed.
Refill or consider installation of hand sanitation near water fountain and safety sanitation signage.
If only hand dryers are available; consider adding paper towels and waste receptacles to improve hand sanitation after turning on and off water.
Clean, wipe down and sanitize all waste receptacles inside and out, replacing liners as warranted.
Wipe down any common area furniture, stools, benches, shower chairs, etc.
AQUATIC CENTER:
Ensure facilities are clean and sanitized and check for mold and mildew growth.
Clean and sanitize all high-touch areas, counters, railings, etc.
Clean and sanitize all pool furniture.
Clean and prep deck surfaces.